## 2015
# | Tool | Description | Type | Reported | Ticket | Feedback
1 | OmegaT | Incorrect display of RTL segments in the Fuzzy Matches pane | BUG | Yes | https://sourceforge.net/p/omegat/bugs/558/ | Didier: can be fixed
2 | Okapi | Filter configuration file is not multiplatform | BUG | Yes
3 | OmegaT | Same colors for auto and enforce matches | BUG | Yes |  | Didier: €500
4 | OmegaT | Direction of Arabic text in fuzzy matches
other bidi issues?
Long segments in Arabic not wrapped in the Fuzzy Matches pane (therefore not readable)
|  | Add TA notes to XLIFF-based projects |  |  |  | get notes from excel, add them to project_save
| OmegaT | Open zipped project from OmegaT withouth unzipping first | RFF
| OmegaT | Segment number per file?

## 2022
Created | # | Tool | Title | Type | Status | Developer | Cost | Comments
TOTAL |  |  |  |  | WIP |  | 3430
2022-07-15 | #43 | Okapi plugin | Tag tooltips do not show the locked text | Bug | Open! | Denis | 1320 | Denis has opened a pull request #16 for it and sent a manual build of plugin with Okapi dependency at c5fa867 commit. To be tested.
2022-07-01 |  | OmegaT | scripts and support with scripting |  | Resolved | Kos | 330 | No ticket
2022-06-28 | #38 | Okapi plugin | OpenXML filter for OmegaT gives error when opening Excel file with embedded HTML | Bug | Open! | Kuro | 1000 | Quote TBC. Re-test with latest version of Okapi plugin. Transferred from Okapi issue #1020.
2022-06-27 | #1621 | OmegaT | Add notes as <note> in target XLIFF file | RFF | Open! | Thomas |  | Green light pending
2022-05-14 | #37 | Okapi plugin | HTML sub-filter in JSON filter not working in OmegaT | Bug | Resolved | Denis |  | Blocking issue for translation JSON files with embedded HTML content in OmegaT. Same as OmegaT #1097. Fixed by Denis Konovalenko in June 2022 (cost: 540, payable by ACER). However, deployment issues remain because Okapi has dropped support for Java 8 while OmegaT is not shipped yet with JRE for Java 11. The patched plugin does not work with OmegaT unless OmegaT is run with Java 11, which therefore needs to be installed manually and OmegaT configured to run with that version.
2022-04-08 | #36 | Okapi plugin | Alternative translations do not work for repetitions within paragraphs | Bug | Open! | Denis? | 40 | Same as OmegaT #1616, not clear whether this needs to be fixed in OmegaT or in the Okapi filter or in both.
2022-05-31 | #1101 | OmegaT | No ID-bound matching in /tm/tmx2source | RFE | Resolved? | Thomas | 0 | The issue prevents ID-specific translation notes.
2022-05-24 | #1099 | OmegaT | Absolute paths used in search results from TMs | Bug | Resolved | Hiroshi |  | Minor improvement to save space and see more clearly where matches come from. Hiroshi fixed it.
2022-05-24 | #1098 | OmegaT | The "file names" option does not work in search results from TMs | Bug | Resolved | Hiroshi |  | Hiroshi fixed it.
2022-05-12 | #1617 | OmegaT | RFE: handling ID-bound alternative translations more efficiently | RFE | Open |  |  | Originally reported as Okapi 1106.
2022-03-02 | #1092 | OmegaT | Enforced ID-bound alternative translations not recognized | Bug | Resolved |  |  | With Aaron's tips I could find the issue and propose a fix. Fixed in 5.8.1.
2022-02-22 | #1128 | Okapi | Table filter: Merge step does not keep edited translation | Bug | Open! |  |  | Online exchange at https://groups.google.com/g/okapi-users/c/lBo0LRASJyA/m/viK3SfsiBAAJ?utm_medium=email&utm_source=footer
2022-02-21 | #1090 | OmegaT | Fails to load TM using <ph> tags | Bug | Open
2022-02-16 | #1608 | OmegaT | Add notes to the translator in /tm/notes/foo.tmx | RFF | Open! | Thomas | 260 | This would be necessary (or very handy) in projects where we need to use second source for a reference version, and it would be confusing to use the same space for translation notes.
2022-01-19 | #35 | Okapi plugin | Improve tags conversion to match OmegaT tags better | RFE | Open? |  |  | Online discussion: https://groups.google.com/g/okapi-users/c/de5LTH7hP4g/m/PysP0msQBwAJ?utm_medium=email&utm_source=footer
-
2021-09-24 | #1070 | OmegaT | Unexpected enforced translation (first match) in OmegaT 4.3 | Bug | Open
2021-09-21 | #1592 | OmegaT | Option to choose how matches are sorted (asc or desc) | RFE | Open~
2021-09-21 | #1591 | OmegaT | Option to export project's master TMs when pressing Ctrl+D | RFF | Open
2021-06-25 | #1578 | OmegaT | Do not propose source text as match from other languages | RFF | Open
2021-05-10 | #41 | Okapi plugin | Unable to set <EMPTY> translation in OmegaT with Okapi filter OpenXML | Bug | Open? |  |  | Transferred from Okapi issue #1055
2021-05-09 | #42 | Okapi plugin | Error parsing XML content (with OpenXML filter in OmegaT) | Bug | Open! | Denis | 480 | Transferred from Okapi issue #1054
2021-05-09 | #1566 | OmegaT | Replace glossary hits when inserting fuzzy match | RFF | Open
2021-05-05 | #1565 | OmegaT | Give each segment a unique ID | RFE | Open!! |  |  | Very important, lack of unique segment ID is a common source of support requests and we spend a great deal of time tweaking source files to allow the creation of alternative translations. The problem is mitigated whenever we can use an Okapi filter (OpenXML, HTML, etc.) but Okapi filters sometimes have other issues
2021-04-30 | #1046 | OmegaT | Glossary has wrong encoding for non-ASCII characters | Bug | Rejected
2021-03-02 | #1038 | OmegaT | "Remove leading/trailing tags" removes tags that are not a tag pair | Bug | Open
2021-02-16 | #1037 | OmegaT | Next Unique Segment shortcut conflicts with Log Out on Mac | Bug | Open
2021-02-04 | #1020 | OmegaT | OpenXML filter for OmegaT gives error when opening Excel file with embedded HTML | Bug | Transfered |  |  | Re-test with latest version of Okapi plugin.
2021-01-22 | #1032 | OmegaT | OmegaT ignores system variable %appdata% on Windows | Bug | Open
2021-01-20 | #1546 | OmegaT | Include OMT plugin in the vanilla installation | RFF | Open! | Thomas
2020-12-10 | #1027 | OmegaT | Resolve Conflicts dialog is useless when enforced matches are updated | Bug | Open |  |  | This feature request aims at preventing the problem that users might inadvertedly create bilingual target files (mixing text in the source and the target languages) if they leave some segments untranslated. OmegaT should not opinionatedly use the source text as the translation if the segment is not translated.
2020-12-10 | #1529 | OmegaT | Folder scripts/application_close to run scripts when OmegaT closes | RFF | Open
-
2020-11-27 | #1527 | OmegaT | Do not export untranslated segments | RFE | Open
2020-11-13 | #558 | OmegaT | Incorrect display of RTL segments in the Fuzzy Matches pane | Bug | Open
2020-11-11 | #1005 | Okapi | XLIFF filter (for OmegaT) hides files with DOCTYPE including URL | Bug | Invalid |  |  | Not reproduceable
2020-10-28 | #1020 | OmegaT | Project file filters are not preserved | Bug | Open
2020-09-29 | #993 | Okapi | Okapi XLIFF filter for OmegaT registers/expects segment IDs that break ID-bound matches | Bug | Open
2020-09-21 | #1520 | OmegaT | Two many locations for user-added plugins | RFE | Rejected |  |  | Closed by the dev team lead (Aaron) with the argument that the two locations are necessary.
2020-09-21 | #1519 | OmegaT | OmegaT uses wrong/old version of plugin in case of conflict | RFE | Open |  |  | Follow up with this.
2020-08-14 | #969 | Okapi | Resname (from XLIFF) appears in the comment field in OmegaT | RFE | Open~ |  |  | Several details could be optimized in the Comments pane vs Segment Properties pane: resname, ID, comment, etc. Test with JSON to XLIFF roundtrip.
2020-07-16 | #1003 | OmegaT | Matches containing non-alphabetical text are ignored in TM leverage | Bug | Open |  |  | Could be fixed with diff-patch-match plugin. WIP with mock-up script.
2020-08-21 | #1015 | OmegaT | Matches ignored if the two locales have the same language subtag | Bug | Open |  |  | Update (2022_06-24): re-test in version 5.8.0.
2020-07-16 | #1002 | OmegaT | Choice of GUI language during re-installation is ignored | Bug | Resolved
2020-07-04 | #1471 | OmegaT | "Full segment" option in search dialog | RFE | Open
2020-06-28 | #1497 | OmegaT | Automatically create system-wide TM repository | RFF | Open |  |  | ticket, + discussion + new discussion -> new ticket??? first wait and see, nothing happened -> then propose sponsorship writing: script to save reading: looking for developer
2020-06-13 | #947 | Okapi | OpenXML Filter: improve the segmentation quality and merge with complex script formatting | RFE | Open
2020-04-27 | #933 | Okapi | OpenXML filter: formatting issues in Arabic translation (RTL) | Bug | Resolved |  |  | On hold, TBC whether Word is the formatting for coding guides in PISA25. As soon as it's confirmed, this ticket would have highest priority.
2020-04-26 | #932 | Okapi | Hook for OmegaT translation kit not working anymore | Bug | Open! |  |  | Follow up with this.
2020-04-15 | #931 | Okapi | OpenXML Filter: remove redundant BIDI properties clarification in RTL | RFE | Open
2020-04-08 | #987 | OmegaT | "Use as default translation" does not work | Bug | Open
2020-03-01 | #988 | OmegaT | RLE and LRE control characters not visible in editor | Bug | Resolved
2020-02-24 | #982 | OmegaT | Layout issues in target Word files in Arabic | Bug | Open
2020-01-27 | #979 | OmegaT | Arabic fuzzy matches not wrapped in FM pane | Bug | Open
2020-01-27 | #977 | OmegaT | Character and tag are glued together in Arabic | Bug | Open
2020-01-22 | #975 | OmegaT | ID-binding context damaged with Olifant-edited TMX files | Bug | Open
-
2018-04-13 | #23 | Okapi plugin | Translation registered as same as source not taken into account | Bug | Open! | Kuro
2018-04-13 | #22 | Okapi plugin | Segment set as <EMPTY> not empty in XLIFF | Bug | Fixed? | Kuro
2017-04-17 | #18 | Okapi plugin | Set the state of the target to 'translated' when saving | RFE | Open! | Kuro?
2006-11-07 | #245 | OmegaT | Formatting shortcuts | RFE | Open

## ETS
# | Tool | Project | Subject | Description | Reported | Onboarded | Confirmed