## 2015
# | Tool | Description | Type | Reported | Ticket | Feedback
1 | OmegaT | Incorrect display of RTL segments in the Fuzzy Matches pane | BUG | Yes | https://sourceforge.net/p/omegat/bugs/558/ | Didier: can be fixed
2 | Okapi | Filter configuration file is not multiplatform | BUG | Yes
3 | OmegaT | Same colors for auto and enforce matches | BUG | Yes |  | Didier: €500
4 | OmegaT | Direction of Arabic text in fuzzy matches
other bidi issues?
Long segments in Arabic not wrapped in the Fuzzy Matches pane (therefore not readable)
|  | Add TA notes to XLIFF-based projects |  |  |  | get notes from excel, add them to project_save
| OmegaT | Open zipped project from OmegaT withouth unzipping first | RFF
| OmegaT | Segment number per file?

## 2022
Created | # | Tool | Title | Type | Status
TOTAL 2023 |  |  |  |  | WIP
2023-08-07 | #1213 | OmegaT | Selection of match for pre-translation varies through different OS's | BUG | Open!!!
2023-08-07 | #1212 | OmegaT | Random selection of match for pre-translation depending on TMX file paths | BUG | Open!!!
2023-07-05 |  | OmegaT | Adapt customization script to work in version 6.1 |  | Resolved
2023-07-17 | #1202 | OmegaT | Error 403 when accessing different repo with different creds in same domain | BUG | Open!
2023-07-12 | #27 | TmxCommentsProvider | T&A notes: T&A note is "null" if the target language doesn't match | RFE | Open!
2023-07-12 | #26 | TmxCommentsProvider | T&A notes: source text in notes/notes.tmx used as the note | RFE | Open!
2023-07-11 | #1201 | OmegaT | -1 instead of repo name in repository credentials | BUG | Open!
2023-07-11 | #1200 | OmegaT | Closing a new project does not register pre-populated translations | BUG | Open!
2023-07-03 | #1708 | OmegaT | Improve colors in the list of project files | RFE | Open
2023-06-27 | #1185 | OmegaT | Saving does not register pre-translation in new projects | BUG | Open!!
2023-06-17 | #11 | plugin-omt-package | NoClassDefFoundError when packing project in OmegaT 6.1.0 | BUG | Resolved
2023-05-23 | #1309 | Okapi | XML filter does not extract resname if unit contains HTML block-level tags | BUG | Open!!
2023-05-23 | #1176 | OmegaT | The COMPILE event is fired *after* the target commit | BUG | Resolved
2023-05-18 | #1171 | OmegaT | Enforced translations lose background color | BUG | Open
2023-05-03 | #1164 | OmegaT | Auto-populated translations disappear when a segment gets activated | BUG | Open!!!
2023-05-03 | #9 | plugin-omt-package | Add property in config to remove mappings (to pack as offline project) | RFE | Resolved
2023-04-28 | #1163 | OmegaT | Project not loaded if it contains DTD internal entities | BUG | Resolved
2023-04-24 | #1161 | OmegaT | "Set empty translation" does not work in XML file | BUG | Open
2023-04-12 | #1690 | OmegaT | "Commit target files" also commits stats file to repo | RFE | Open!!!
2023-03-11 |  | Okapi plugin | Backported latest Okapi plugin to JDK 8 |  | Resolved
2023-03-22 | #1155 | OmegaT | Option "Insert the source text" enabled on its own | BUG | Open
2023-03-08 | #1150 | OmegaT | Tags cannot be deleted in RTL languages | BUG | Open!!
2023-03-08 | #1151 | OmegaT | Tag drag-and-drop duplicates tag in RTL text | BUG | Open!!
2023-03-06 | #1200 | Okapi | XML filter adds tags arounb nnbsp by default | BUG | Open+
2023-02-24 | #1681 | OmegaT | Straight quotes match curly quotes | RFE | Open
2023-02-15 | #1142 | OmegaT | Translation displayed as source text if state="final" with Okapi XLIFF filter | BUG | Open
2023-02-13 | #8 | plugin-omt-package | Only __DEFAULT__ project folders are packed correctly | RFE | Open
2023-02-10 | #1674 | OmegaT | Remove custom tags issues and flagged text from mandatory tag check | RFE | Open!
2023-02-07 | #1672 | OmegaT | Hide tag-only segments | RFE | Open!!
2023-01-26 | #1669 | OmegaT | Remove leadinga and trailing tags with Okapi filters | RFE | Open!!
2023-01-26 | #1670 | OmegaT | Reuse credentials in team projects | RFE | Resolved
2023-01-23 | #1184 | Okapi | Fractions in Word file are not extracted | BUG | Open!
2023-01-22 | #49 | Okapi plugin | Use resname as segment identifier (instead of correlative number) | RFE | Resolved
2023-01-20 | #1140 | OmegaT | Context-bound matches are ignored in /tm/auto | Bug | Resolved
2023-01-03 | #1132 | OmegaT | OmegaT CLI gets stuck at missing empty folders when run on team project | Bug | Open!
TOTAL 2022 |  |  |  |  | WIP
2022-11-14 | #1125 | OmegaT | OmegaT's main window is sent to unplugged monitor | Bug | Open
2022-10-24 | #1641 | OmegaT | Navigate between segments inserted from /tm/auto and /tm/enforce | RFE | Open
2022-10-21 | #1124 | OmegaT | Local project does not update after remote masking some files | Bug | Open!!
2022-10-10 | #1122 | OmegaT | Tag color is obfuscated if target language uses RTL script | Bug | Open?
2022-07-15 | #43 | Okapi plugin | Tag tooltips do not show the locked text | Bug | Resolved
373466 | #1622 | OmegaT | Option to give or revoke full writing access to team project users | RFF | Open
2022-07-01 |  | OmegaT | scripts and support with scripting |  | Resolved
2022-06-28 | #38 | Okapi plugin | OpenXML filter for OmegaT gives error when opening Excel file with embedded HTML | Bug | Open!
2022-06-27 | #1621 | OmegaT | Add notes as `<note>` in target XLIFF file | RFF | Open!
2022-05-12 | #1616 | OmegaT | Non-unique IDs when segmenting text blocks extracted by Okapi OpenXML | RFE | Open!
2022-05-14 | #37 | Okapi plugin | HTML sub-filter in JSON filter not working in OmegaT | Bug | Resolved
2022-04-08 | #36 | Okapi plugin | Alternative translations do not work for repetitions within paragraphs | Bug | Open!
2022-05-31 | #1101 | OmegaT | No ID-bound matching in /tm/tmx2source | RFE | Resolved?
2022-05-24 | #1099 | OmegaT | Absolute paths used in search results from TMs | Bug | Resolved
2022-05-24 | #1098 | OmegaT | The "file names" option does not work in search results from TMs | Bug | Resolved
2022-05-12 | #1617 | OmegaT | handling ID-bound alternative translations more efficiently | RFE | Open
2022-03-02 | #1092 | OmegaT | Enforced ID-bound alternative translations not recognized | Bug | Resolved
2022-02-22 | #1128 | Okapi | Table filter: Merge step does not keep edited translation | Bug | Open!
2022-02-21 | #1090 | OmegaT | Fails to load TM using `<ph>` tags | Bug | Open
2022-02-16 | #1608 | OmegaT | Add notes to the translator in /tm/notes/foo.tmx | RFF | Resolved
2022-01-19 | #35 | Okapi plugin | Improve tags conversion to match OmegaT tags better | RFE | Open?
-
2021-09-24 | #1070 | OmegaT | Unexpected enforced translation (first match) in OmegaT 4.3 | Bug | Open
2021-09-21 | #1592 | OmegaT | Option to choose how matches are sorted (asc or desc) | RFE | Open~
2021-09-21 | #1591 | OmegaT | Option to export project's master TMs when pressing Ctrl+D | RFF | Open
2021-06-25 | #1578 | OmegaT | Do not propose source text as match from other languages | RFF | Open
2021-05-10 | #41 | Okapi plugin | Unable to set `<EMPTY>` translation in OmegaT with Okapi filter OpenXML | Bug | Open?
2021-05-09 | #42 | Okapi plugin | Error parsing XML content (with OpenXML filter in OmegaT) | Bug | Open!
2021-05-09 | #1566 | OmegaT | Replace glossary hits when inserting fuzzy match | RFF | Open
2021-05-05 | #1565 | OmegaT | Give each segment a unique ID | RFE | Open!!
2021-04-30 | #1046 | OmegaT | Glossary has wrong encoding for non-ASCII characters | Bug | Rejected
2021-03-24 | #1559 | OmegaT | Validate tags when leaving a segment only for that segment | RFF | Open!
2021-03-02 | #1038 | OmegaT | "Remove leading/trailing tags" removes tags that are not a tag pair | Bug | Open
2021-02-16 | #1037 | OmegaT | Next Unique Segment shortcut conflicts with Log Out on Mac | Bug | Open
2021-02-04 | #1020 | OmegaT | OpenXML filter for OmegaT gives error when opening Excel file with embedded HTML | Bug | Transfered
2021-01-22 | #1032 | OmegaT | OmegaT ignores system variable %appdata% on Windows | Bug | Open
2021-01-20 | #1546 | OmegaT | Include OMT plugin in the vanilla installation | RFF | Open!
2020-12-10 | #1027 | OmegaT | Resolve Conflicts dialog is useless when enforced matches are updated | Bug | Open
2020-12-10 | #1529 | OmegaT | Folder scripts/application_close to run scripts when OmegaT closes | RFF | Open
-
2020-11-27 | #1527 | OmegaT | Do not export untranslated segments | RFE | Open
2020-11-13 | #558 | OmegaT | Incorrect display of RTL segments in the Fuzzy Matches pane | Bug | Open
2020-11-11 | #1005 | Okapi | XLIFF filter (for OmegaT) hides files with DOCTYPE including URL | Bug | Invalid
2020-10-28 | #1020 | OmegaT | Project file filters are not preserved | Bug | Open
2020-09-29 | #993 | Okapi | Okapi XLIFF filter for OmegaT registers/expects segment IDs that break ID-bound matches | Bug | Open
2020-09-21 | #1520 | OmegaT | Two many locations for user-added plugins | RFE | Rejected
2020-09-21 | #1519 | OmegaT | OmegaT uses wrong/old version of plugin in case of conflict | RFE | Resolved
2020-08-14 | #969 | Okapi | Resname (from XLIFF) appears in the comment field in OmegaT | RFE | Open~
2020-07-16 | #1003 | OmegaT | Matches containing non-alphabetical text are ignored in TM leverage | Bug | Resolved
2020-08-21 | #1015 | OmegaT | Matches ignored if the two locales have the same language subtag | Bug | Open
2020-07-16 | #1002 | OmegaT | Choice of GUI language during re-installation is ignored | Bug | Resolved
2020-07-04 | #1471 | OmegaT | "Full segment" option in search dialog | RFE | Open
2020-06-28 | #1497 | OmegaT | Automatically create system-wide TM repository | RFF | Open
2020-06-13 | #947 | Okapi | OpenXML Filter: improve the segmentation quality and merge with complex script formatting | RFE | Open
2020-04-27 | #933 | Okapi | OpenXML filter: formatting issues in Arabic translation (RTL) | Bug | Resolved
2020-04-26 | #932 | Okapi | Hook for OmegaT translation kit not working anymore | Bug | Open!
2020-04-15 | #931 | Okapi | OpenXML Filter: remove redundant BIDI properties clarification in RTL | RFE | Open
2020-04-08 | #987 | OmegaT | "Use as default translation" does not work | Bug | Open
2020-03-01 | #988 | OmegaT | RLE and LRE control characters not visible in editor | Bug | Resolved
2020-02-24 | #982 | OmegaT | Layout issues in target Word files in Arabic | Bug | Open
2020-01-27 | #979 | OmegaT | Arabic fuzzy matches not wrapped in FM pane | Bug | Open
2020-01-27 | #977 | OmegaT | Character and tag are glued together in Arabic | Bug | Open
2020-01-22 | #975 | OmegaT | ID-binding context damaged with Olifant-edited TMX files | Bug | Open
2019-04-29 | #1445 | OmegaT | Multiple-value input/editor for custom tags | RFF | Open
2019-04-29 | #1444 | OmegaT | Enhancing number update when inserting fuzzy matches | RFF | Open
2019-03-16 | #1427 | OmegaT | Project-specific custom tag definition | RFF | Open
-
2018-04-13 | #23 | Okapi plugin | Translation registered as same as source not taken into account | Bug | Open!
2018-04-13 | #22 | Okapi plugin | Segment set as `<EMPTY>` not empty in XLIFF | Bug | Fixed?
2017-04-17 | #18 | Okapi plugin | Set the state of the target to 'translated' when saving | RFE | Open!
2016-03-28 | #1207 | OmegaT | Treat custom tags as OmegaT tags when calculating match estimates | RFF | Open
2006-11-07 | #245 | OmegaT | Formatting shortcuts | RFE | Open

## ETS
# | Tool | Project | Subject | Description | Reported | Onboarded | Confirmed